## Sheet1
Test scenario ID | Test Scenario name | Test case ID | Test Case Description | Created By | Creation Date | Execute By | Execution Date
TS_1.0 | To verify URL | TC_1 | Verify valid Swag Labs page URL. | Nikita | 24/11/2023
|  | TC_2 | Verfiy Invalid Sawg Labs Page URL. | Nikita
TS_2.0 | Verify UI/UX on "Swag Labs". | TC_3 | Verify all the texts and buttons of swag labs page are Gramatically correct and do not have spelling misteks. | Nikita
|  | TC_4 | Verify all the fields of swag labs page are provided with enough space between them | Nikita
|  | TC_5 | Verfiy all the fields and texts on swag labs page are standard size and format. | Nikita
|  | TC_6 | Verify cross Icon on swag Labs page. | Nikita
|  | TC_7 | Verify weather all buttons are having in proper positon or not. | Nikita
Nikita
TS_3.0 | Verify the log in Functionaliy on "Swag labs" page with standard_user and secret_sauce | TC_8 | Validate Login functionality on swag labs with standard_user with valid log in credentials. | Nikita
|  | TC_9 | Validate Login functionality on swag labs with standard_user with Invalid log in credentials. | Nikita
|  | TC_10 | Verify the cross on Username and password. | Nikita
|  | TC_11 | Verify weather the login credentials are Reset or not. | Nikita
TS_3.1 | Verify the different Functionalites on "Product" of "Swag labs" with standard_user and secret_sauce. | TC_12 | Verify that the products on product page are matches with their respective image or not. | Nikita
|  | TC_13 | Verify the "Add cart" button on products module is working or not. | Nikita
|  | TC_14 | verify the "Remove" Button on products module is working or not. | Nikita
|  | TC_15 | Verify weather the filtering on products modules of Swag labs page is working or not. | Nikita
|  | TC_16 | Verify weather the Add Cart Button shows the changes after adding or removing of product. | Nikita
TS_3.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with standard_user and secret_sauce. | TC_17 | Verify the Added items are Displyed or not in your cart. | Nikita
|  | TC_18 | Verfiy weather the product details are displayed or not by cliking on the added items. | Nikita
|  | TC_19 | Verify weather the "Continue shopping" button is working or not. | Nikita
|  | TC_20 | Verify weather the "Remove" button shows the changes after removing the product. | Nikita
|  | TC_21 | Verify weather the "Verifyout" button shows the your information on clikcing on the button. | Nikita
TS_3.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with standard_user and secret_sauce. | TC_22 | Verify Your Information with Invalid data. | Nikita
|  | TC_23 | Verify Your Information with valid data. | Nikita
|  | TC_24 | Verify "Countinue" button. | Nikita
|  | TC_25 | Verify "Cancel" button. | Nikita
TS_3.4 | Verify the different Functionalites on "Overview" of "Swag labs" with standard_user and secret_sauce | TC_26 | Verify weather the Detailed description of Verify out item is displayed or not | Nikita
|  | TC_27 | verify the cancel button. | Nikita
|  | TC_28 | Verify the Finish button. | Nikita
TS_3.5 | Verify the different Functionalites on "complete" of "Swag labs" with standard_user and secret_sauce | TC_29 | Verify the Back Home Button its shows the product page of swag labs page. | Nikita
TS_3.6 | Verify the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | TC_30 | Verify that Log In pag displyed after clicking on the Logout button. | Nikita
Nikita
TS _4.0 | Verify the log in Functionaliy on "Swag labs" page with locked_out_user and secret_sauce | TC_31 | Validate Login functionality on swag labs with locked_out_user with valid log in credentials. | Nikita
|  | TC_32 | Validate Login functionality on swag labs with locked_out_user with Invalid log in credentials. | Nikita
|  | TC_33 | Verify the Cross button on user name and password field | Nikita
|  | TC_34 | verfiy weather the the Log In credentials are Reset or not. | Nikita
Nikita
TS_5.0 | Verify the log in Functionaliy on "Swag labs" page with problem_user and secret_sauce | TC_35 | Validate Login functionality on swag labs with problem_user with valid log in credentials. | Nikita
|  | TC_36 | Validate Login functionality on swag labs with problem_user with Invalid log in credentials. | Nikita
|  | TC_37 | Verify cross icon on username &passwod. | Nikita
|  | TC_38 | Verify weather the login credentials are Reset or not. | Nikita
TS_5.1 | Verify the different Functionalites on "Product" of "Swag labs" with problem_user and secret_sauce. | TC_39 | Verify that the products on product page are matches with their respective image or not. | Nikita
|  | TC_40 | Verify the "Add to cart" button on products module of Swag Labs pge is working or not. | Nikita
|  | TC_41 | Verify the "Remove" button on products module of Swag Labs pge is working or not. | Nikita
|  | TC_42 | Verfiy weather the filtering on products module of Swag Labs is working or not. | Nikita
|  | TC_43 | Verify weather the Cart Button shows the changes after adding or removing of product. | Nikita
TS_5.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with problem_user and secret_sauce. | TC_44 | Verify the Added items are Displyed or not in your cart. | Nikita
|  | TC_45 | Verfiy weather the product details are displayed or not by cliking on the added items. | Nikita
|  | TC_46 | Verify weather the "Continue shopping" button is working or not. | Nikita
|  | TC_47 | Verify weather the "Remove" button shows the changes after removing the product. | Nikita
|  | TC_48 | "Verify weather the "Verifyout" button shows the your information on clikcing on the button." | Nikita
TS_5.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with problem_user and secret_sauce. | TC_49 | Verify Your Information with valid data. | Nikita
|  | TC_50 | Verify "Countinue" button. | Nikita
|  | TC_51 | Verify "Cancel" button. | Nikita
|  | TC_52 |  | Nikita
TS_5.4 | Verify the Logout Functionality On "Swag Labs" page with problem_user and secret_sauce | TC_53 | Verify that Log In page is displayed after clicking on Logout. | Nikita
TS_6.0 | Verify the Log In Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | TC_54 | Validate the Log In Functionality On Swag Labs page with performance_glitch_user and secret_sauce with Valid Log In Credentials. | Nikita
|  | TC_55 | Validate the Log In Functionality On Swag Labs page With performance_glitch_user and secret_sauce with Invalid Log In Credentials. | Nikita
|  | TC_56 | Verify the "Cross" on Username And Password Field.
|  | TC_57 | Verify whether the Log In credentials Reset or not.
TS_6.1 | Verify the different Functionalities on "Product" of Swag Labs With performance_glitch_user and secret_sauce | TC_58 | Verify that the Items on Product page matches with their respective images.
|  | TC_59 | Verify whether the "Add to Cart" Button On Products module of Swag Labs is working or not.
|  | TC_60 | Verify whether the "Remove" Button on Products module of Swag Labs is working or not.
|  | TC_61 | Verify whether the filtering on products module of Swag Labs is working or not.
|  | TC_62 | Verify whether the Cart button shows Changes or not after adding or removing the products in cart
TS_6.2 | Verify the different Functionalities on "Your Cart"of Swag Labs With performance_glitch_user and secret_sauce | TC_63 | Verify the Added Items are "Displayed" or not in Your Cart.
|  | TC_64 | Verify whether Product details are displayed or not by clicking on the added Items.
|  | TC_65 | Verify the added Items are removed or not on Clicking "Remove" Button.
|  | TC_66 | Verify "Continue Shopping" Button.
|  | TC_67 | Verify the "Verifyout" Button.
TS_6.3 | Verify the different Functionalities on "Your Information" Page of Swag Labs With performance_glitch_user and secret_sauce | TC_68 | Verify Your Information with Valid Data.
|  | TC_69 | Verify Your Information with Invalid Data.
|  | TC_70 | Verify the "Cancel" Button.
|  | TC_71 | Verify the "Continue" Button.
TS_6.4 | Verify the different Functionalities on "Verifyout: Overview" Page of Swag Labs With performance_glitch_user and secret_sauce | TC_72 | Verify whether the Detailed description of Verifyout items is displayed or Not.
|  | TC_73 | Verify the "Cart" Button.
|  | TC_74 | Verify the "Cancel" Button.
|  | TC_75 | Verify the "Finish" Button.
TS_6.5 | Verify the Logout Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | TC_76 | Verify that Log In page is displayed after clicking on Logout.
TS_6.6 | Verify the Performance Functionality of "Swag Labs" page with performance_glitch_user and secret_sauce | TC_77 | Verify the Performance of all the pages.
TS_7.0 | Verify the Log In Functionality On "Swag Labs" page with error_user and secret_sauce | TC_78 | Validate Login functionality on swag labs with error_user with valid log in credentials.
|  | TC_79 | Validate Login functionality on swag labs with problem_user with Invalid log in credentials.
|  | TC_80 | Verify cross icon on username &passwod.
|  | TC_81 | Verify weather the login credentials are Reset or not.
TS_7.1 | Verify the different Functionalites on "Product" of "Swag labs" with error_user and secret_sauce. | TC_82 | Verify that the products on product page are matches with their respective image or not.
|  | TC_83 | Verify the "Add to cart" button on products module of Swag Labs pge is working or not.
|  | TC_84 | Verify the "Remove" button on products module of Swag Labs pge is working or not.
|  | TC_85 | Verfiy weather the filtering on products module of Swag Labs is working or not.
|  | TC_86 | Verify weather the Cart Button shows the changes after adding or removing of product.
TS_7.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with error_user and secret_sauce. | TC_87 | Verify the Added items are Displyed or not in your cart.
|  | TC_88 | Verfiy weather the product details are displayed or not by cliking on the added items.
|  | TC_89 | Verify weather the "Continue shopping" button is working or not.
|  | TC_90 | Verify weather the "Remove" button shows the changes after removing the product.
|  | TC_91 | "Verify weather the "Verifyout" button shows the your information on clikcing on the button."
TS_7.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with error_user and secret_sauce. | TC_92 | Verify Your Information with Invalid data.
|  | TC_93 | Verify Your Information with valid data.
|  | TC_94 | Verify "Countinue" button.
|  | TC_95 | Verify "Cancel" button.
TS_7.4 | Verify the different Functionalites on "Overview" of "Swag labs" with error_user and secret_sauce | TC_96 | Verify weather the Detailed description of Verify out item is displayed or not
|  | TC_97 | Verify the cart button.
|  | TC_98 | verify the cancel button.
|  | TC_99 | Verify the Finish button.
TS_7.5 | Verify the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | TC_100 | Verify that Log In pag displyed after clicking on the Logout button.
TS_8.0 | Verify the log in Functionaliy on "Swag labs" page with visual_user and secret_sauce | TC_101 | Validate Login functionality on swag labs with standard_user with valid log in credentials.
|  | TC_102 | Validate Login functionality on swag labs with standard_user with Invalid log in credentials.
|  | TC_103 | Verify the cross on Username and password.
TS_8.1 | Verify the different Functionalites on "Product" of "Swag labs" with visual_user and secret_sauce. | TC_104 | Verify weather the login credentials are Reset or not.
|  | TC_105 | Verify that the products on product page are matches with their respective image or not.
|  | TC_106 | Verify the "Add cart" button on products module is working or not.
|  | TC_107 | verify the "Remove" Button on products module is working or not.
|  | TC_108 | Verify weather the filtering on products modules of Swag labs page is working or not.
|  | TC_109 | Verify weather the Add Cart Button shows the changes after adding or removing of product.
TS_8.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with visual_user and secret_sauce. | TC_110 | Verify the Added items are Displyed or not in your cart.
|  | TC_111 | Verfiy weather the product details are displayed or not by cliking on the added items.
|  | TC_112 | Verify weather the "Continue shopping" button is working or not.
|  | TC_113 | Verify weather the "Remove" button shows the changes after removing the product.
|  | TC_114 | Verify weather the "Verifyout" button shows the your information on clikcing on the button.
TS_8.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with visual_user and secret_sauce. | TC_115 | Verify Your Information with Invalid data.
|  | TC_116 | Verify Your Information with valid data.
|  | TC_117 | Verify "Countinue" button.
|  | TC_118 | Verify "Cancel" button.
TS_8.4 | Verify the different Functionalites on "Overview" of "Swag labs" with visual_user and secret_sauce | TC_119 | Verify weather the Detailed description of Verify out item is displayed or not
|  | TC_120 | Verify the cart button.
|  | TC_121 | verify the cancel button.
|  | TC_122 | Verify the Finish button.
TS_8.5 | Verify the different Functionalites on "complete" of "Swag labs" with visual_user and secret_sauce | TC_123 | Verify the Back Home Button its shows the product page of swag labs page.
TS_8.6 | Verify the different Functionalites on "Logout" of "Swag labs" with visual_userand secret_sauce | TC_124 | Verify that Log In pag displyed after clicking on the Logout button.

## Sheet2
Test scenario id | Test case Id | Test scenario Desription | Test case description | Module | Pre condition | test data | Step to reproduce | Expected Result | Actual result | status | Created by | Created date | Executed by | Excuation date
TS_1.0 | TC_1 | To verify URL | Verify valid Swag Labs page URL. |  | Connection and valid URL required. | https://www.saucedemo.com/ | check the internet connection. open the broweser. wite the URL. | web page should be open. | web page is open. | Pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_2 |  | Verfiy Invalid Sawg Labs Page URL. |  | Connection and Invalid URL required. | https://www.saucedemo.com/v1/ | check the internet connection. open the broweser. wite the URL. | web page should not be open. | web page is not open. | Pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_2.0 | TC_3 | Verify UI/UX on "Swag Labs". | check all the texts and buttons of swag labs page are Gramatically correct and do not have spelling misteks. |  | Web should be available. |  | Check the texts and buttons of swag labs page are Gramatically correct and do not have spelling misteks. | the texts and buttons of swag labs page should be Gramatically correct | the texts and buttons of swag labs page is Gramatically correct | Pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_4 |  | Verify all the fields of swag labs page are provided with enough space between them |  |  |  | Check all the fields of swag labs page are provided with enough space between them | all the fields of swag labs page should be provided with enough space between them | all the fields of swag labs page is provided with enough space between them | Pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_5 |  | Verfiy all the fields and texts on swag labs page are standard size and format. |  |  |  | Check all the fields and texts on swag labs page are standard size and format. | all the fields and texts on swag labs page should be standard size and format. | all the fields and texts on swag labs page is in standard size and format. | Pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_6 |  | Verify cross Icon on swag Labs page. |  |  |  | Check cross Icon on swag Labs page. | Croos Icon should be there. | Cross Icon is there. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_7 |  | Verify weather all buttons are having in proper positon or not. |  |  |  | Check weather all buttons are having in proper position. | All buttons are should be in proper position. | All buttons are having not in proper position. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.0 | TC_8 | Verify the log in Functionaliy on "Swag labs" page with standard_user and secret_sauce | Verify Login functionality on swag labs with standard_user with valid log in credentials. | LOG_IN | user is already register. | Data:- Username :- standard_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. |  | User is Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_9 |  | Verify Login functionality on swag labs with standard_user with Invalid log in credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_10 |  | Verify the cross on Username and password. | LOG_IN |  | N/A | 1.Click on the cross Icon displayed after entering the invalid credentials. | User name & password field should reset when click on cross Icon. | Userr name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_11 |  | Verify weather the login credentials are Reset or not. | LOG_IN |  | N/A | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.1 | TC_12 | Verify the different Functionalites on "Product" of "Swag labs" with standard_user and secret_sauce. | Verify that the products on product page are matches with their respective image or not. | Product page | User is alredy Log_in. | N/A | 1.Check the products on product page are matches with their respective image or not. | The products on product page Sould be matches with their respective image . | The products on product page is matches with their respective image. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_13 |  | Verify the "Add cart" button on products module is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Add cart" button on products module are working or not. | The "Add cart" button on products module Should be working . | The "Add cart" button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_14 |  | verify the "Remove" Button on products module is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Remove" Button on products module are working or not. | The "Remove" Button on products module should be working | The "Remove" Button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_15 |  | Verify weather the filtering on products modules of Swag labs page is working or not. | Product page | User is alredy Log_in. | Refer test data sheet | Check the filtering on products modules are working or not. | The filtering on products modules should be working | The filtering on products modules is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_16 |  | Verify weather the Add Cart Button shows the changes after adding or removing of product. | Product page | product is alredy in added in your cart. | N/A | Check the Add Cart Button shows the changes after adding or removing of product. | The Add Cart Button Should be shows the changes after adding or removing of product. | The Add Cart Button is shows the changes after adding or removing of product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.2 | TC_18 | Verify the different Functionalites on "Your Cart" of "Swag labs" with standard_user and secret_sauce. | Verify the Added items are Displyed or not in your cart. | Your Cart page | product is alredy in added in your cart. |  | Check the Added items are Displyed or not in your cart. | The Added items Should be Displyed in your cart. | The Added items is Displyed in your cart. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_19 |  | Verfiy weather the product details are displayed or not by cliking on the added items. | Your Cart page | product is alredy in added in your cart. |  | Check the product details are displayed or not by cliking on the added items. | The product details Should be displayed by cliking on the added items. | The product details is displayed by cliking on the added items. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_20 |  | Verify weather the "Continue shopping" button is working or not. | Your Cart page | product is alredy in added in your cart. |  | Check the "Continue shopping" button is working or not. | The "Continue shopping" button should be working. | The "Continue shopping" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_21 |  | Verify weather the "Remove" button shows the changes after removing the product. | Your Cart page | product is alredy in added in your cart. |  | Check the "Remove" button shows the changes after removing the product. | The "Remove" button Should be shows the changes after removing the product. | The "Remove" button is shows the changes after removing the product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_22 |  | Verify weather the "Verifyout" button shows the your information on clikcing on the button. | Your Cart page | product is alredy in added in your cart. |  | Check the "Checkout" button shows the your information on clikcing on the button. | The "Verifyout" button Should be shows the your information on clikcing on the button. | The "Verifyout" button is shows the your information on clikcing on the button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.3 | TC_23 | Verify the different Functionalites on "Your Information" with standard_user and secret_sauce. | Verify Your Information with Invalid data. | Verifyout page | product is alredy in added in your cart. |  | Check Your Information with Invalid data. | Your Information should not be continue successfully. | Your Information s is continue successfully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_24 |  | Verify Your Information with valid data. | Verifyout page | product is alredy in added in your cart. | Data:- First name:- amit Last name :- m Zip/postal code:- 400701 | 1. Enter the valid First name. 2.Enter the valid Last name. 3. Click on continue button. | Your Informationshould be continue successfully. | Your Information is continue successfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_25 |  | Verify "Countinue" button. | Verifyout page | product is alredy in added in your cart. |  | Check "Countinue" button. | The "Countinue" button Should be working. | The "Countinue" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_26 |  | Verify "Cancel" button. | Verifyout page | product is alredy in added in your cart. |  | Check "Cancel" button. | The "Cancel" button Should be working. | The "Cancel" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.4 | TC_27 | Verify the different Functionalites on "Overview" of "Swag labs" with standard_user and secret_sauce | Verify weather the Detailed description of Verify out item is displayed or not |  |  |  | 1. Open Checkout: Overview page. 2. Check the Detailed description of Checkout item is displayed or not | The Detailed description of Verify out item should be displayed . | The Detailed description of Verify out item is displayed . | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_28 |  | verify the cancel button. |  |  |  | Check the cancel button. | The cancel button should be working succesfully. | The cancel button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_29 |  | Verify the Finish button. |  |  |  | Check the Finish button. | The Finish button should be working succesfully. | The Finish button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.5 | TC_30 | Verify the different Functionalites on "complete" of "Swag labs" with standard_user and secret_sauce | Verify the Back Home Button its shows the product page of swag labs page. |  |  |  | Check the Back Home Button its shows the product page of swag labs page. | The Back Home Button should be shows the product page of swag labs page. | The Back Home Button is shows the product page of swag labs page. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_3.6 | TC_31 | Verify the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | Verify that Log In page displyed after clicking on the Logout button. |  |  |  | Check Log In page displyed after clicking on the Logout button. | Log In page should be displyed after clicking on the Logout button. | Log In page is displyed after clicking on the Logout button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS _4.0 | TC_32 | Verify the log in Functionaliy on "Swag labs" page with locked_out_user and secret_sauce. | Validate Login functionality on swag labs with locked_out_user with valid log in credentials. | LOG_IN | user is already register. | Data:- Username :- locked_out_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. | User should be Log_In Succefully. | User is not Log_In Succefully its shows this massege "Sorry, this user has been locked out". | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_33 |  | Validate Login functionality on swag labs with locked_out_user with Invalid log in credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_34 |  | Verify the Cross button on user name and password field | LOG_IN |  | N/A | 1.Click on the cross Icon displyed after entering the invalid credentials. 2. Check weather the corresponding field are reset or not. | User name & password field should reset when click on cross Icon. | Userr name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_35 |  | verfiy weather the the Log In credentials are Reset or not. | LOG_IN |  | N/A | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_5.0 | TC_36 | Verify the log in Functionaliy on "Swag labs" page with problem_user and secret_sauce | Validate Login functionality on swag labs with problem_user with valid log in credentials. | LOG_IN | user is already register. | Data:- Username :- problem_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. | User should be Log_In Succefully. | User is Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_37 |  | Validate Login functionality on swag labs with problem_user with Invalid log in credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_38 |  | Verify cross icon on username &passwod. | LOG_IN |  | N/A | 1.Click on the cross Icon displyed after entering the invalid credentials. Check weather the corresponding field are reset or not. | USer name & password field should reset when click on cross Icon. | User name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_39 |  | Verify weather the login credentials are Reset or not. | LOG_IN |  | N/A | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_5.1 | TC_40 | Verify the different Functionalites on "Product" of "Swag labs" with problem_user and secret_sauce. | Verify that the products on product page are matches with their respective image or not. | Product page |  |  | 1.Check the products on product page are matches with their respective image or not. | The products on product page Sould be matches with their respective image . | The products on product page IS NOT matches with their respective image . | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_41 |  | Verify the "Add to cart" button on products module of Swag Labs pge is working or not. | Product page |  |  | Check the "Add cart" button on products module are working or not. | The "Add cart" button on products module Should be working . | The "Add cart" button on products module IS NOT working . | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_42 |  | Verify the "Remove" button on products module of Swag Labs pge is working or not. | Product page |  |  | Check the "Remove" Button on products module are working or not. | The "Remove" Button on products module should be working | The "Remove" Button on products module IS NOT working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_43 |  | Verfiy weather the filtering on products module of Swag Labs is working or not. | Product page |  |  | Check the filtering on products modules are working or not. | The filtering on products modules should be working | The filtering on products modules IS NOT working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_44 |  | Verify weather the Cart Button shows the changes after adding or removing of product. | Product page |  |  | Check the Add Cart Button shows the changes after adding or removing of product. | The Add Cart Button Should be shows the changes after adding or removing of product. | The Add Cart Button is shows the changes after adding or removing of product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_5.2 | TC_45 | Verify the different Functionalites on "Your Cart" of "Swag labs" with problem_user and secret_sauce. | Verify the Added items are Displyed or not in your cart. | Your Cart page | product is alredy in added in your cart. |  | Check the Added items are Displyed or not in your cart. | The Added items Should be Displyed in your cart. | The Added items is Displyed in your cart. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_46 |  | Verfiy weather the product details are displayed or not by cliking on the added items. | Your Cart page | product is alredy in added in your cart. |  | Check the product details are displayed or not by cliking on the added items. | The product details Should be displayed by cliking on the added items. | The product details is displayed by cliking on the added items. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_47 |  | Verify weather the "Continue shopping" button is working or not. | Your Cart page | product is alredy in added in your cart. |  | Check the "Continue shopping" button is working or not. | The "Continue shopping" button should be working. | The "Continue shopping" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_48 |  | Verify weather the "Remove" button shows the changes after removing the product. | Your Cart page | product is alredy in added in your cart. |  | Check the "Remove" button shows the changes after removing the product. | The "Remove" button Should be shows the changes after removing the product. | The "Remove" button is shows the changes after removing the product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_49 |  | "Verify weather the "Verifyout" button shows the your information on clikcing on the button." | Your Cart page | product is alredy in added in your cart. |  | Check the "Checkout" button shows the your information on clikcing on the button. | The "Verifyout" button Should be shows the your information on clikcing on the button. | The "Verifyout" button is shows the your information on clikcing on the button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_5.3 | TC_50 | Verify the different Functionalites on "Your Information" of "Swag labs" with problem_user and secret_sauce. | Verify Your Information with valid data. |  |  |  | 1. Enter the valid First name. 2.Enter the valid Last name. 3. Click on continue button. | Checkout should be continue succefully. | On Checkout page the username & password is Taken properly. | Fail
| TC_51 |  | Verify "Countinue" button. |  |  |  | Check the Continue button. | The Continue button should be working succesfully. | The Continue button is not working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_52 |  | Verify "Cancel" button. |  |  |  | Check the Cancel button. | The Cancel button should be working succesfully. | The Cancel button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_5.4 | TC_53 | Verify the Logout Functionality On "Swag Labs" page with problem_user and secret_sauce | Verify that Log In page is displayed after clicking on Logout. |  |  |  | Check Log In page displyed after clicking on the Logout button. | Log In page should be displyed after clicking on the Logout button. | Log In page is displyed after clicking on the Logout button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.0 | TC_54 | Verify the Log In Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | Validate the Log In Functionality On Swag Labs page with Valid Log In Credentials | LOG_IN | user is already register. | Data:- Username :- performance_glitch_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. | User should be Log_In Succefully. | User is Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_55 |  | Validate the Log In Functionality On Swag Labs page With Invalid Log In Credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_56 |  | Verify the "Cross" on Username And Password Field. | LOG_IN |  |  | 1.Click on the cross Icon displyed after entering the invalid credentials. Check weather the corresponding field are reset or not. | User name & password field should reset when click on cross Icon. | User name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_57 |  | Verify whether the Log In credentials Reset or not. | LOG_IN |  |  | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.1 | TC_58 | Verify the different Functionalities on "Product" of Swag Labs With performance_glitch_user and secret_sauce | Verify that the Items on Product page matches with their respective images. | Product page | User is alredy Log_in. | N/A | Check the products on product page are matches with their respective image or not. | The products on product page Sould be matches with their respective image . | The products on product page is matches with their respective image. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_59 |  | Verify whether the "Add to Cart" Button On Products module of Swag Labs is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Add cart" button on products module are working or not. | The "Add cart" button on products module Should be working . | The "Add cart" button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_60 |  | Verify whether the "Remove" Button on Products module of Swag Labs is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Remove" Button on products module are working or not. | The "Remove" Button on products module should be working | The "Remove" Button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_61 |  | Verify whether the filtering on products module of Swag Labs is working or not. | Product page | User is alredy Log_in. | Refer test data sheet | Check the filtering on products modules are working or not. | The filtering on products modules should be working | The filtering on products modules is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_62 |  | Verify whether the Cart button shows Changes or not after adding or removing the products in cart | Product page | product is alredy in added in your cart. | N/A | Check the Add Cart Button shows the changes after adding or removing of product. | The Add Cart Button Should be shows the changes after adding or removing of product. | The Add Cart Button is shows the changes after adding or removing of product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.2 | TC_63 | Verify the different Functionalities on "Your Cart"of Swag Labs With performance_glitch_user and secret_sauce | Verify the Added Items are "Displayed" or not in Your Cart. | Your Cart page | product is alredy in added in your cart. |  | Check the Added items are Displyed or not in your cart. | The Added items Should be Displyed in your cart. | The Added items is Displyed in your cart. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_64 |  | Verify whether Product details are displayed or not by clicking on the added Items. | Your Cart page | product is alredy in added in your cart. |  | Check the product details are displayed or not by cliking on the added items. | The product details Should be displayed by cliking on the added items. | The product details is displayed by cliking on the added items. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_65 |  | Verify the added Items are removed or not on Clicking "Remove" Button. | Your Cart page | product is alredy in added in your cart. |  | Check the "Continue shopping" button is working or not. | The "Continue shopping" button should be working. | The "Continue shopping" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_66 |  | Verify "Continue Shopping" Button. | Your Cart page | product is alredy in added in your cart. |  | Check the "Remove" button shows the changes after removing the product. | The "Remove" button Should be shows the changes after removing the product. | The "Remove" button is shows the changes after removing the product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_67 |  | Verify the "Verifyout" Button. | Your Cart page | product is alredy in added in your cart. |  | Check the "Checkout" button shows the your information on clikcing on the button. | The "Verifyout" button Should be shows the your information on clikcing on the button. | The "Verifyout" button is shows the your information on clikcing on the button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.3 | TC_68 | Verify the different Functionalities on "Your Information" Page of Swag Labs With performance_glitch_user and secret_sauce | Verify Your Information with Valid Data. | Verifyout page | product is alredy in added in your cart. |  | Check Your Information with Invalid data. | Checkout should not be continue succefully. | checkout is continue succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_69 |  | Verify Your Information with Invalid Data. | Verifyout page | product is alredy in added in your cart. | Data:- First name:- amit Last name :- m Zip/postal code:- 400701 | 1. Enter the valid First name. 2.Enter the valid Last name. 3. Click on continue button. | Verifyout should be continue succefully. | checkout is continue succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_70 |  | Verify the "Cancel" Button. | Verifyout page | product is alredy in added in your cart. |  | Check "Countinue" button. | The "Countinue" button Should be working. | The "Countinue" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_71 |  | Verify the "Continue" Button. | Verifyout page | product is alredy in added in your cart. |  | Check "Cancel" button. | The "Cancel" button Should be working. | The "Cancel" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.4 | TC_72 | Verify the different Functionalities on "Verifyout: Overview" Page of Swag Labs With performance_glitch_user and secret_sauce | Verify whether the Detailed description of Verifyout items is displayed or Not. |  |  |  | 1. Open Checkout: Overview page. 2. Check the Detailed description of Checkout item is displayed or not | The Detailed description of Verify out item should be displayed . | The Detailed description of Verify out item is displayed . | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_73 |  | Verify the "Cart" Button. |  |  |  | Check the cancel button. | The cancel button should be working succesfully. | The cancel button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_74 |  | Verify the "Cancel" Button. |  |  |  | Check the Finish button. | The Finish button should be working succesfully. | The Finish button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_75 |  | Verify the "Finish" Button. |  |  |  | Check the Back Home Button its shows the product page of swag labs page. | The Back Home Button should be shows the product page of swag labs page. | The Back Home Button is shows the product page of swag labs page. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.5 | TC_76 | Verify the Logout Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | Verify that Log In page is displayed after clicking on Logout. |  |  |  | Check Log In page displyed after clicking on the Logout button. | Log In page should be displyed after clicking on the Logout button. | Log In page is displyed after clicking on the Logout button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_6.6 | TC_77 | Verify the Performance Functionality of "Swag Labs" page with performance_glitch_user and secret_sauce | Verify the Performance of all the pages. |  |  |  | Check the Performance of all the pages. | The Performance of all the pages should be working properly. | The Performance of all the pages is slow.
TS_7.0 | TC_78 | Verify the Log In Functionality On "Swag Labs" page with error_user and secret_sauce | Validate Login functionality on swag labs with error_user with valid log in credentials. | LOG_IN | user is already register. | Data:- Username :- standard_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. | User should be Log_In Succefully. | User is Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_79 |  | Validate Login functionality on swag labs with problem_user with Invalid log in credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_80 |  | Verify cross icon on username &passwod. | LOG_IN |  | N/A | 1.Click on the cross Icon displyed after entering the invalid credentials. Check weather the corresponding field are reset or not. | USer name & password field should reset when click on cross Icon. | Userr name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_81 |  | Verify weather the login credentials are Reset or not. | LOG_IN |  | N/A | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_7.1 | TC_82 | Verify the different Functionalites on "Product" of "Swag labs" with error_user and secret_sauce. | Verify that the products on product page are matches with their respective image or not. | Product page | User is alredy Log_in. | N/A | 1.Check the products on product page are matches with their respective image or not. | The products on product page Sould be matches with their respective image . | The products on product page is matches with their respective image. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_83 |  | Verify the "Add to cart" button on products module of Swag Labs pge is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Add cart" button on products module are working or not. | The "Add cart" button on products module Should be working . | The "Add cart" button on products module is not working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_84 |  | Verify the "Remove" button on products module of Swag Labs pge is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Remove" Button on products module are working or not. | The "Remove" Button on products module should be working | The "Remove" Button on products module is not working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_85 |  | Verfiy weather the filtering on products module of Swag Labs is working or not. | Product page | User is alredy Log_in. | Refer test data sheet | Check the filtering on products modules are working or not. | The filtering on products modules should be working | The filtering on products modules is not working | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_86 |  | Verify weather the Cart Button shows the changes after adding or removing of product. | Product page | product is alredy in added in your cart. | N/A | Check the Add Cart Button shows the changes after adding or removing of product. | The Add Cart Button Should be shows the changes after adding or removing of product. | The Add Cart Button is shows the changes after adding or removing of product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_7.2 | TC_87 | Verify the different Functionalites on "Your Cart" of "Swag labs" with error_user and secret_sauce. | Verify the Added items are Displyed or not in your cart. | Your Cart page | product is alredy in added in your cart. |  | Check the Added items are Displyed or not in your cart. | The Added items Should be Displyed in your cart. | The Added items is Displyed in your cart. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_88 |  | Verfiy weather the product details are displayed or not by cliking on the added items. | Your Cart page | product is alredy in added in your cart. |  | Check the product details are displayed or not by cliking on the added items. | The product details Should be displayed by cliking on the added items. | The product details is displayed by cliking on the added items. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_89 |  | Verify weather the "Continue shopping" button is working or not. | Your Cart page | product is alredy in added in your cart. |  | Check the "Continue shopping" button is working or not. | The "Continue shopping" button should be working. | The "Continue shopping" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_90 |  | Verify weather the "Remove" button shows the changes after removing the product. | Your Cart page | product is alredy in added in your cart. |  | Check the "Remove" button shows the changes after removing the product. | The "Remove" button Should be shows the changes after removing the product. | The "Remove" button is shows the changes after removing the product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_91 |  | "Verify weather the "Verifyout" button shows the your information on clikcing on the button." | Your Cart page | product is alredy in added in your cart. |  | Check the "Checkout" button shows the your information on clikcing on the button. | The "Verifyout" button Should be shows the your information on clikcing on the button. | The "Verifyout" button is shows the your information on clikcing on the button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_7.3 | TC_92 | Verify the different Functionalites on "Your Information" of "Swag labs" with error_user and secret_sauce. | Verify Your Information with Invalid data. | Checkout page | product is alredy in added in your cart. |  | Check Your Information with Invalid data. | Checkout should not be continue succefully. | Checkout is continue succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_93 |  | Verify Your Information with valid data. | Checkout page | product is alredy in added in your cart. | Data:- First name:- amit Last name :- m Zip/postal code:- 400701 | 1. Enter the valid First name. 2.Enter the valid Last name. 3. Click on continue button. | Checkout should be continue succefully. | Checkout is continue succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_94 |  | Verify "Countinue" button. | Checkout page | product is alredy in added in your cart. |  | Check "Countinue" button. | The "Countinue" button Should be working. | The "Countinue" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_95 |  | Verify "Cancel" button. | Checkout page | product is alredy in added in your cart. |  | Check "Cancel" button. | The "Cancel" button Should be working. | The "Cancel" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_7.4 | TC_96 | Verify the different Functionalites on "Overview" of "Swag labs" with error_user and secret_sauce | Verify weather the Detailed description of Verify out item is displayed or not |  |  |  | 1. Open Checkout: Overview page. 2. Check the Detailed description of Checkout item is displayed or not | The Detailed description of Verify out item should be displayed . | The Detailed description of Verify out item is displayed . | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_97 |  | Verify the cart button. |  |  |  | Check the cart button. | the cart button should be working properly. | the cart button is working properly. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_98 |  | verify the cancel button. |  |  |  | Check the cancel button. | The cancel button should be working succesfully. | The cancel button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_99 |  | Verify the Finish button. |  |  |  | Check the Finish button. | The Finish button should be working succesfully. | The Finish button is not working succesfully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_7.5 | TC_100 | Verify the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | Verify that Log In pag displyed after clicking on the Logout button. |  |  |  | Check Log In page displyed after clicking on the Logout button. | Log In page should be displyed after clicking on the Logout button. | Log In page is displyed after clicking on the Logout button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.0 | TC_101 | Verify the log in Functionaliy on "Swag labs" page with visual_user and secret_sauce | Validate Login functionality on swag labs with visual_user with valid log in credentials. | LOG_IN | user is already register. | Data:- Username :- visual_user Password:- secret_sauce | 1. Enter the valid user name. 2.Enter the valid password. 3. Click on Log_In button. | User should be Log_In Succefully. | User is Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_102 |  | Validate Login functionality on swag labs with visual_user with Invalid log in credentials. | LOG_IN |  | Data:- Username :- invalid_user Password:- Inavalid_sauce | 1. Enter the Invalid user name. 2.Enter the Invalid password. 3. Click on Log_In button. | User should Not Log_In Succefully. | User is not Log_In Succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_103 |  | Verify the cross on Username and password. | LOG_IN |  | N/A | 1.Click on the cross Icon displyed after entering the invalid credentials. Check weather the corresponding field are reset or not. | USer name & password field should reset when click on cross Icon. | Userr name & password field is not reset when click on cross Icon. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.1 | TC_104 |  | Verify weather the login credentials are Reset or not. | LOG_IN |  | N/A | 1. Check weather the corresponding field are reset or not. | Log_In credentials should be reset succefully. | Log_In credentials is not reset succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_105 | Verify the different Functionalites on "Product" of "Swag labs" with visual_user and secret_sauce. | Verify that the products on product page are matches with their respective image or not. | Product page | User is alredy Log_in. | N/A | 1.Check the products on product page are matches with their respective image or not. | The products on product page Sould be matches with their respective image . | The products on product page is not matches with their respective image. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_106 |  | Verify the "Add cart" button on products module is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Add cart" button on products module are working or not. | The "Add cart" button on products module Should be working . | The "Add cart" button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_107 |  | verify the "Remove" Button on products module is working or not. | Product page | User is alredy Log_in. | N/A | Check the "Remove" Button on products module are working or not. | The "Remove" Button on products module should be working | The "Remove" Button on products module is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_108 |  | Verify weather the filtering on products modules of Swag labs page is working or not. | Product page | User is alredy Log_in. | Refer test data sheet | Check the filtering on products modules are working or not. | The filtering on products modules should be working | The filtering on products modules is working | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_109 |  | Verify weather the Add Cart Button shows the changes after adding or removing of product. | Product page | product is alredy in added in your cart. | N/A | Check the Add Cart Button shows the changes after adding or removing of product. | The Add Cart Button Should be shows the changes after adding or removing of product. | The Add Cart Button is shows the changes after adding or removing of product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.2 | TC_110 | Verify the different Functionalites on "Your Cart" of "Swag labs" with visual_user and secret_sauce. | Verify the Added items are Displyed or not in your cart. | Your Cart page | product is alredy in added in your cart. |  | Check the Added items are Displyed or not in your cart. | The Added items Should be Displyed in your cart. | The Added items is Displyed in your cart. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_111 |  | Verfiy weather the product details are displayed or not by cliking on the added items. | Your Cart page | product is alredy in added in your cart. |  | Check the product details are displayed or not by cliking on the added items. | The product details Should be displayed by cliking on the added items. | The product details is displayed by cliking on the added items. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_112 |  | Verify weather the "Continue shopping" button is working or not. | Your Cart page | product is alredy in added in your cart. |  | Check the "Continue shopping" button is working or not. | The "Continue shopping" button should be working. | The "Continue shopping" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_113 |  | Verify weather the "Remove" button shows the changes after removing the product. | Your Cart page | product is alredy in added in your cart. |  | Check the "Remove" button shows the changes after removing the product. | The "Remove" button Should be shows the changes after removing the product. | The "Remove" button is shows the changes after removing the product. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_114 |  | Verify weather the "Verifyout" button shows the your information on clikcing on the button. | Your Cart page | product is alredy in added in your cart. |  | Check the "Checkout" button shows the your information on clikcing on the button. | The "Verifyout" button Should be shows the your information on clikcing on the button. | The "Verifyout" button is shows the your information on clikcing on the button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.3 | TC_115 | Verify the different Functionalites on "Your Information" of "Swag labs" with visual_user and secret_sauce. | Verify Your Information with Invalid data. | Checkout page | product is alredy in added in your cart. |  | Check Your Information with Invalid data. | Checkout should not be continue succefully. | Checkout is continue succefully. | Fail | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_116 |  | Verify Your Information with valid data. | Checkout page | product is alredy in added in your cart. | Data:- First name:- amit Last name :- m Zip/postal code:- 400701 | 1. Enter the valid First name. 2.Enter the valid Last name. 3. Click on continue button. | Checkout should be continue succefully. | Checkout is continue succefully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_117 |  | Verify "Countinue" button. | Checkout page | product is alredy in added in your cart. |  | Check "Countinue" button. | The "Countinue" button Should be working. | The "Countinue" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_118 |  | Verify "Cancel" button. | Checkout page | product is alredy in added in your cart. |  | Check "Cancel" button. | The "Cancel" button Should be working. | The "Cancel" button is working. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.4 | TC_119 | Verify the different Functionalites on "Overview" of "Swag labs" with visual_user and secret_sauce | Verify weather the Detailed description of Verify out item is displayed or not |  |  |  | 1. Open Checkout: Overview page. 2. Check the Detailed description of Checkout item is displayed or not | The Detailed description of Verify out item should be displayed . | The Detailed description of Verify out item is displayed . | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_120 |  | Verify the cart button. |  |  |  | Check the cart button. | The cart button should be working succesfully. | The cart cart button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_121 |  | verify the cancel button. |  |  |  | Check the cancel button. | The cancel button should be working succesfully. | The cancel button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
| TC_122 |  | Verify the Finish button. |  |  |  | Check the Finish button. | The Finish button should be working succesfully. | The Finish button is working succesfully. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.5 | TC_123 | Verify the different Functionalites on "complete" of "Swag labs" with visual_user and secret_sauce | Verify the Back Home Button its shows the product page of swag labs page. |  |  |  | Check the Back Home Button its shows the product page of swag labs page. | The Back Home Button should be shows the product page of swag labs page. | The Back Home Button is shows the product page of swag labs page. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023
TS_8.6 | TC_124 | Verify the different Functionalites on "Logout" of "Swag labs" with visual_userand secret_sauce | Verify that Log In page displyed after clicking on the Logout button. |  |  |  | Check Log In page displyed after clicking on the Logout button. | Log In page should be displyed after clicking on the Logout button. | Log In page is displyed after clicking on the Logout button. | pass | Nikita | 24/11/2023 | Nikita | 24/11/2023

## RTM
Requirment ID | Requirment Description | Test scenario | Test case ID | Status
1 | TS_1.0 | To Check URL | TC_1 | pass
TC_2
2 | TS_2.0 | Verify UI/UX on "Swag Labs". | TC_3 | Pass
|  |  | TC_4 | Pass
|  |  | TC_5 | Pass
|  |  | TC_6 | pass
|  |  | TC_7 | Fail
3 | TS_3.0 | Check the log in Functionaliy on "Swag labs" page with standard_user and secret_sauce | TC_8 | pass
|  |  | TC_9 | pass
|  |  | TC_10 | Fail
|  |  | TC_11 | Fail
4 | TS_3.1 | Check the different Functionalites on "Product" of "Swag labs" with standard_user and secret_sauce. | TC_12 | pass
|  |  | TC_13 | pass
|  |  | TC_14 | pass
|  |  | TC_15 | pass
|  |  | TC_16 | pass
5 | TS_3.2 | Check the different Functionalites on "Your Cart" of "Swag labs" with standard_user and secret_sauce. | TC_18 | pass
|  |  | TC_19 | pass
|  |  | TC_20 | pass
|  |  | TC_21 | pass
|  |  | TC_22 | pass
6 | TS_3.3 | Check the different Functionalites on "Your Information" with standard_user and secret_sauce. | TC_23 | Fail
|  |  | TC_24 | pass
|  |  | TC_25 | pass
|  |  | TC_26 | pass
7 | TS_3.4 | Check the different Functionalites on "Overview" of "Swag labs" with standard_user and secret_sauce | TC_27 | pass
|  |  | TC_28 | pass
|  |  | TC_29 | pass
8 | TS_3.5 | Check the different Functionalites on "complete" of "Swag labs" with standard_user and secret_sauce | TC_30 | pass
9 | TS_3.6 | Check the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | TC_31 | pass
10 | TS _4.0 | Check the log in Functionaliy on "Swag labs" page with locked_out_user and secret_sauce | TC_32 | Fail
|  |  | TC_33 | pass
|  |  | TC_34 | Fail
|  |  | TC_35 | Fail
11 | TS_5.0 | Verify the log in Functionaliy on "Swag labs" page with problem_user and secret_sauce | TC_36 | pass
|  |  | TC_37 | pass
|  |  | TC_38 | Fail
|  |  | TC_39 | Fail
12 | TS_5.1 | Verify the different Functionalites on "Product" of "Swag labs" with problem_user and secret_sauce. | TC_40 | Fail
|  |  | TC_41 | Fail
|  |  | TC_42 | Fail
|  |  | TC_43 | Fail
|  |  | TC_44 | pass
13 | TS_5.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with problem_user and secret_sauce. | TC_45 | pass
|  |  | TC_46 | pass
|  |  | TC_47 | pass
|  |  | TC_48 | pass
|  |  | TC_49 | pass
14 | TS_5.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with problem_user and secret_sauce. | TC_50 | Fail
|  |  | TC_51 | Fail
|  |  | TC_52 | pass
15 | TS_5.4 | Verify the Logout Functionality On "Swag Labs" page with problem_user and secret_sauce | TC_53 | pass
16 | TS_6.0 | Verify the Log In Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | TC_54 | pass
|  |  | TC_55 | pass
|  |  | TC_56 | Fail
|  |  | TC_57 | Fail
17 | TS_6.1 | Verify the different Functionalities on "Product" of Swag Labs With performance_glitch_user and secret_sauce | TC_58 | pass
|  |  | TC_59 | pass
|  |  | TC_60 | pass
|  |  | TC_61 | pass
|  |  | TC_62 | pass
18 | TS_6.2 | Verify the different Functionalities on "Your Cart"of Swag Labs With performance_glitch_user and secret_sauce | TC_63 | pass
|  |  | TC_64 | pass
|  |  | TC_65 | pass
|  |  | TC_66 | pass
|  |  | TC_67 | pass
19 | TS_6.3 | Verify the different Functionalities on "Your Information" Page of Swag Labs With performance_glitch_user and secret_sauce | TC_68 | Fail
|  |  | TC_69 | pass
|  |  | TC_70 | pass
|  |  | TC_71 | pass
20 | TS_6.4 | Verify the different Functionalities on "Verifyout: Overview" Page of Swag Labs With performance_glitch_user and secret_sauce | TC_72 | pass
|  |  | TC_73 | pass
|  |  | TC_74 | pass
|  |  | TC_75 | pass
21 | TS_6.5 | Verify the Logout Functionality On "Swag Labs" page with performance_glitch_user and secret_sauce | TC_76 | pass
22 | TS_6.6 | Verify the Performance Functionality of "Swag Labs" page with performance_glitch_user and secret_sauce | TC_77 | fail
23 | TS_7.0 | Verify the Log In Functionality On "Swag Labs" page with error_user and secret_sauce | TC_78 | pass
|  |  | TC_79 | pass
|  |  | TC_80 | Fail
|  |  | TC_81 | Fail
24 | TS_7.1 | Verify the different Functionalites on "Product" of "Swag labs" with error_user and secret_sauce. | TC_82 | pass
|  |  | TC_83 | Fail
|  |  | TC_84 | Fail
|  |  | TC_85 | Fail
|  |  | TC_86 | pass
25 | TS_7.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with error_user and secret_sauce. | TC_87 | pass
|  |  | TC_88 | pass
|  |  | TC_89 | pass
|  |  | TC_90 | pass
|  |  | TC_91 | pass
26 | TS_7.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with error_user and secret_sauce. | TC_92 | Fail
|  |  | TC_93 | pass
|  |  | TC_94 | pass
|  |  | TC_95 | pass
27 | TS_7.4 | Verify the different Functionalites on "Overview" of "Swag labs" with error_user and secret_sauce | TC_96 | pass
|  |  | TC_97 | pass
|  |  | TC_98 | pass
|  |  | TC_99 | Fail
28 | TS_7.5 | Verify the different Functionalites on "Logout" of "Swag labs" with standard_user and secret_sauce | TC_100 | pass
29 | TS_8.0 | Verify the log in Functionaliy on "Swag labs" page with visual_user and secret_sauce | TC_101 | pass
|  |  | TC_102 | pass
|  |  | TC_103 | Fail
|  |  | TC_104 | Fail
30 | TS_8.1 | Verify the different Functionalites on "Product" of "Swag labs" with visual_user and secret_sauce. | TC_105 | Fail
|  |  | TC_106 | pass
|  |  | TC_107 | pass
|  |  | TC_108 | pass
|  |  | TC_109 | pass
31 | TS_8.2 | Verify the different Functionalites on "Your Cart" of "Swag labs" with visual_user and secret_sauce. | TC_110 | pass
|  |  | TC_111 | pass
|  |  | TC_112 | pass
|  |  | TC_113 | pass
|  |  | TC_114 | pass
32 | TS_8.3 | Verify the different Functionalites on "Your Information" of "Swag labs" with visual_user and secret_sauce. | TC_115 | Fail
|  |  | TC_116 | pass
|  |  | TC_117 | pass
|  |  | TC_118 | pass
33 | TS_8.4 | Verify the different Functionalites on "Overview" of "Swag labs" with visual_user and secret_sauce | TC_119 | pass
|  |  | TC_120 | pass
|  |  | TC_121 | pass
|  |  | TC_122 | pass
34 | TS_8.5 | Verify the different Functionalites on "complete" of "Swag labs" with visual_user and secret_sauce | TC_123 | pass
35 | TS_8.6 | Verify the different Functionalites on "Logout" of "Swag labs" with visual_userand secret_sauce | TC_124 | pass

## defect report
Defect ID | Test_case_ID | Module name | Title | Steps to produce | Expected Result | Actual Result | Status | Severity | Priority | Created By | Date of Reproduce | Comments(suggestion)